Sebastian Brzozowski

Intro to ITWS

Project Management at Kuehchic Desserts

February 23, 2026

Will the company launch before September 1, 2022?

Kuehchic Desserts will fail the September 1 deadline because the team faces structural delays and the plan requires more days than the calendar provides. Starting July 1 and excluding weekends leaves only 44 workdays. However, the project path asks for more than 44 days.

Three business tasks take 30 days total, these tasks alone are the core of the company. Task B3 needs 10 days for legal compliance and regulatory requirements. Task B8 needs 15 days for a test market and result evaluation. Task B9 needs 5 days for the final company launch. These tasks must happen in order. Other steps like recipe preparation A4 and equipment installation A7 add more time. Task A7 requires 6 days alone. The total time pushes past the goal.

Each founder costs 30 dollars per hour. Total costs for ingredients will reach 2,500 dollars only getting more expensive as time goes on and the business scales. The aspect of price as well plays a key role here, cause if your plan takes longer that means more expensive. Shortening your plan, making it faster. Directly helps the business, not only timewise but also .financially.

Shiva Kumar starts late because he finishes an internship in August. As a result, this stops website progress. Task C1 needs 10 days. Task C2 needs 2 days. Task C3 needs 2 days. The website requires these specific steps in order. You must move production to professional facilities quickly so you can leave the kitchen owned by your parents. Buying and installing equipment takes 9 days total. These changes require time for scaling and recipe adjustments. There is not enough time to complete every task.

Instead of using this timeline you should start task C1 in July. Hire a new coder to remove the August bottleneck. Shorten task B8 because the 15-day test is too long. You should run many tests together. Move faster in the kitchen. Order machines while you make products from the kitchen of your parents. This lets task A7 finish early and allows you to move into your space faster. The team should work on weekends. Working on weekends increases expenses but adding 48 hours every week helps. These days provide a buffer. You should find test panels while you make products. Doing tasks at the same time saves time. You are very low on time, and this plan simply is too long and slow for what this business needs.

WORKS CITED

De Meyer, Arnoud. Project Management at Kuehchic Desserts: Refreshing a Traditional Business. Singapore Management University, 2022.