# Project Management at Kuehchic Desserts, Notes

The Vision: Daryl Lim wants to create "less traditional but healthier and more elegant kuehs" to "refresh a traditional business".

The Products: Kueh is a Peranakan staple made with ingredients like "pandan, coconut, rice, tapioca, and palm sugar". Lim’s goal is to make them "attuned to the taste of the millennium generation".

The Business Model: The team decided "Kuehchic would offer trendier kueh with a healthy twist" through an "online shop, making use of existing e-commerce platforms and home delivery services".

Cultural Context: Set in Singapore, where "food was a huge part of the local lifestyle" and the country is known as a "food hub".

### Stakeholder Analysis

Daryl Lim (Co-founder): High influence; he "had to set a strategy to launch his products" and "worked out a schedule for the various necessary tasks".

Sharon Tan (Operations Manager): High importance; she is "in charge of creating an online shop" and developing a "detailed business plan".

Shiva Kumar (IT Support): High technical influence; he was convinced "to help them on a part-time basis" to "develop the basic website with ordering and payment systems".

Lim’s Parents: Moderate importance; they "allowed him to use their kitchen for the launch" but Lim knew he would eventually "have to scale up".

Target Consumers: High importance; the team needed to "test his products with a wider tasting panel" and "panels of consumers in their target market".

### Project Constraints and Requirements

The Triple Constraint: Time is critical because "the team could only start work in July" and Lim wondered if they could launch "before the beginning of September".

Resource Bottleneck: A major hurdle is that Shiva Kumar "could not start before early August" because he was "finishing an internship".

Financials: Labor is valued at "S$30 per hour" for the three founders, and ingredients are estimated not to exceed "S$2,500".

### Key Project Management Terms to Know

Critical Path: Lim specifically asks, "Which tasks are on the critical path?". This refers to the sequence of tasks with zero float that dictates the project end date.

Total Float (Slack): Lim wants to evaluate "what was the total float (slack)?"  to see how much delay the project can withstand.

Free Float: He also wants to know "which task had the highest free float (slack)?", which measures the delay possible without affecting the next task.

### Risks and Management

Project Risks: Lim is concerned about the workload, asking, "Were any of them overloaded?" and whether the "suggested sequencing would work".

Business Risks: Sharon Tan noted they needed to "examine whether the name was acceptable" and ensure products were "easy to produce in large quantities".