Intro to ITWS

ITWS 1100

Spring 2026

Project Management at Kuehchic Desserts: Refreshing a Traditional Business

- Monday February 23, 2026

  - Read and be prepared to discuss the “Project Management at Kuehchic Desserts: Refreshing a Traditional Business” case included in the Course Pack from Harvard Business School Press.

  - Research appropriately outside of the case to support your answers (Note: The case intentionally does not provide “answers” – your research will need to help you both learn definitions/concepts as well as conduct analysis to help you answer the questions).

  - Prepare to answer the following questions related to the case during class: (Do not submit your answers for these questions in writing.  You may however answer and/or take notes and bring to class with you to use for your own reference during the discussion)

    - Who are the stakeholders of this project?

      - How important is this project to each of them?

      - How much influence do they have?

    - The triple constraint in projects is scope, time, and cost.  Which of these three constraints is most important in this case?

    - Define ‘Critical Path’, ‘Free Float’, and ‘Total Float’.

    - Do you agree with the proposed sequencing of tasks?

    - Are there any tasks that Lim forget to include in the task list?

    - Are any of the team members overloaded on work?

    - What are the biggest risks for the project to launch the company (Kuehchic Desserts)?

    - What are the biggest risks for the proposed type of business (boutique dessert company)?

    - What can the project team do to address both types of risk?

  - Submit the answer to the following case question in written form by 11:30 AM on Monday, February 23 on LMS.

    - Since the case is set in 2022, assume the team starts the project on July 1, 2022, based on the tasks Lim defined, and follows the rules of not working on weekends but working on official holidays.

      - Will the company be launched prior to September 1, 2022?

        - If you believe yes, why?  What did the team do correctly to be able to achieve this timeline?

        - If you believe no, why not?  What would you advise be done in order to achieve the timeline?

    - The length of these written answers should be one to two pages, single spaced with 12-point font and standard margins.

    - Include your name, the course name, the case title, and date in a header at the top of the assignment.

    - State and clearly answer the written question.

    - Use qualitative and quantitative arguments from the case and other sources as needed to support your answer.

    - Use professional English language, spelling, grammar, and referencing.  Use the MLA citation format or equivalent.  See RPI’s Writing Lab for any additional assistance at https://successcenter.rpi.edu/ and/or the associated MLA citation page: https://owl.purdue.edu/owl/research_and_citation/mla_style/mla_formatting_and_style_guide/mla_formatting_and_style_guide.html